INSTRUMENT 5

Management Report by Exception

Three pages maximum. Written by the Medical Director with the Afya operational leads.

Template issued by Consult for Africa for the Board of Havana Specialist Hospital Limited.

Adopted by the Board on [date]. Administered by the Company Secretary.

Complete every field in [square brackets]. Delete the italic guidance before circulating.

| Period | [quarter] |
| --- | --- |
| Prepared by | [Medical Director] with [Afya operational lead] |
| Date | [date] |

1. The three things the board should know

Three bullets. If a director reads nothing else, this is what they must not miss. At least one should be uncomfortable.

2. Performance against plan

Reference the dashboard. Narrate only what is off plan. For every exception, answer the four standing questions in the table below.

| Exception | Why different from plan? | One-off or trend? | What is being done, by whom, by when? | What would make it worse? |
| --- | --- | --- | --- | --- |

3. What went well, briefly

Two or three. Boards that only ever hear problems stop being told about them.

4. What is coming

The next quarter: what management expects, and what could knock it off course.

5. Where we need the board

| Decisions requested | [cross-referenced to board papers] |
| --- | --- |
| Steers wanted | [where management wants direction] |
| Where we feel blocked | [say it here, plainly] |

6. Declared escalations since the last meeting

What crossed a threshold, when it was escalated, to whom, and how it was resolved. Nil returns are stated as nil, not left blank.

| What happened | Threshold crossed | Date | Escalated to | Resolution |
| --- | --- | --- | --- | --- |

Section 6 is the honesty test of the whole system. If serious things happened and this section is empty, the escalation thresholds are not being used, and that is a governance failure whatever the underlying result looked like.